## WO
Project Work Order
Job Number | 3260509 |  |  | Address | 1319 M-45 | Date Issued |  | 2026-05-14
Project Name | RLE Concrete |  |  |  | Grand Rapids, MI | Work Order # |  | 1
Project Manager | Justin Edmondson |  |  | Super | JK Sr | Material Delivery Date |  | SOF
Division | 3 |  |  |  |  | Approved Shop Drawings |  | YES
Description of Work
Type | Elevation | Quantity | Fab | Comments |  |  | Date Reqd | Start Date | Date Complete | Initial
Storefront | 1 | 1 | Assemble | Door built by VOS |  |  | 2026-06-08

## Fab WO
Fabrication Work Order
|  | Job Name |  | RLE Concrete |  |  | PM | Justin Edmondson |  | WO | 1 | Completion Request | 2026-06-08
Cut List | Completed |  | Date/Initial |  |  |  | Fab Check List
| Yes | N/A
[6 empty] | Storefront |  |  | Curtain Wall |  |  |  | Entrances
Material Pick List | Completed |  | Date/Initial
| Yes | N/A |  |  | Elevation Validation |  | Elevation Validation |  |  |  |  | Elevation Validation
[5 empty] | Horizontals caulked |  | Shear Blocks installed |  |  |  |  | Shear Blocks Install for Sill
Programing | Completed |  | Date/Initial |  | Gasket installed and caulked |  | Perimeter Gasket Validation |  |  |  |  | Wire Installed (When Requested)
| Yes | N/A |  |  | Water Divertors installed |  | Pressure Plate/Cap Weep Holes |  |  |  |  | Transom Gutter sealed
[5 empty] | Sub-Sill Gasket Pulled | [6 empty] | Transom Jambs sealed
Saw | Completed |  | Date/Initial |  | Sub-Sill Prepped and End damned | [6 empty] | HDW Installed
| Yes | N/A |  |  | Perimeter Plastic Installed + Caulked | [6 empty] | Instructions Included
Anchor Plates Installed - 2 per DLO
CNC | Completed |  | Date/Initial
| Yes | N/A
Fabrication | Completed |  | Date/Initial
| Yes | N/A
Material Picked and Staged |  |  | Date/Initial
| Yes | N/A
Notes:

## Data
Kit | Storefront | Yes
Assemble | Curtain Wall | No
Hardware | Window Wall
SL Door Frame | Door